## General Info
| Bug severity level | Score Assignment
| Low | 1
| High | 5
| Critical | 10
| Count low | Count High | Count Critical | Score low | Score High | Score Critical
Iteration 1 | 0 | 0 | 0 | 0 | 0 | 0
Iteration 2 | 4 | 4 | 0 | 4 | 20 | 0
Iteration 3 | 1 | 1 | 2 | 1 | 5 | 20
Iteration 4 | 0 | 2 | 2 | 0 | 10 | 20
Iteration 5 | 0 | 3 | 2 | 0 | 15 | 20
Iteration 6 | 0 | 4 | 0 | 0 | 20 | 0
Iteration 7 | 0 | 1 | 2 | 0 | 5 | 20
Iteration 8 | #VALUE!

## Iteration 2
S/N | Bug Description | Bug Location | Severity
1 | Messages on the login page do not get cleared. For example, a successful registration after a failed login attempt will display both "Invalid credentials entered" and "You have successfully registered" simultaneously on the login page | Login page | Low
2 | Users can enter gibberish for the "email" field and the registration is still accepted as valid | Registration page | High
3 | Registering more than 1 account with the exact same username and password combination is possible. This also causes this username and password combination to be unable to login | Login page | High
4 | Searchbar and magnifying glass icon are not properly aligned | Homepage | Low
5 | Variable type for database creation script is too short to support actual length of course names from raw data file | Database creation | High
6 | Node 1 on navigation bar is a dead link that doesn't actually redirect back to homepage as intended | Navigation bar | Low
7 | "Homepage" is a dead link that doesn't actually redirect back to home page as intended | Homepage | Low
8 | Clicking "upload" brings user to profile page instead of upload page | Upload page | High
9
10

## Iteration 3
S/N | Bug Description | Bug Location | Severity
1 | Bootsrap script does not run unless all "skill" columns in the Excel file are populated | Bootstrap | Critical
2 | Bootstrap function cannot be run twice consecutively without clearing database tables first | Bootstrap | High
3 | Registration page crashes because user_id column hasn't been properly integrated with frontend logic | Registration page | Critical
4 | Displayed skills do not align properly and overlap each other | Skills analysis page | Low
5
6
7
8
9
10

## Iteration 4
S/N | Bug Description | Bug Location | Severity | Notes
1 | Implementing the logout functionality meant edits to UserBean.java were necessary. These changes caused the app to crash during runtime | Runtime | Critical
2 | Skills weightage algorithm not working as expected, returning results inconsistent with expected output | Skills analysis | High
3 | Application crashes when deployed and run on LARC servers | Runtime | Critical | Server already deployed a previous-team's app, conflicts in port and firewall rules
4 | After admin uploads the new course design document, the system does not immediately show the newly added results after returning to homepage, need to login again | Runtime | High | Persistence management should be improved.
5
6
7
8
9
10

## Iteration 5
S/N | Bug Description | Bug Location | Severity | Notes
1 | Application crashed when uploaded a non-excel file with exception | Admin upload page | Critical | Improve exception handling
2 | Application uploaded data to the database without verifying content(missing course detail) | Admin upload page | Critical | Improve file integrity checking
3 | Password pannel not ordered and cluttered with normal user credentials | Admin Dashboard | High | Newer sorting technic should be implement into the monitoring script
4 | User profile set up page showing the global value of username | Profile | High | Remove hard-coded global variable in the userbean
5 | Userbean session is hard-coded to a specific user, this is reflected on the welcome screen | Homepage | High | Remove hard-coded global variable in the userbean
6
7
8
9
10

## Iteration 6
S/N | Bug Description | Bug Location | Severity | Notes
1 | Search result page takes a long time in aligning, sorting the contents, decreasing the user experience | Track search result | High | Due to several css and js conflicts in the page, simplify the imported libraries and remove the unused ones.
2 | Website traffic tracking is not displayed properly against the real traffics | Admin Dashboard | High | Integration between the front-end and database writing is misalligned
3 | When the tree diagram is visualised, the jobSense API cannot retrieve data at the same | Track search result | High | Possible cause is conflicting libraries frontend and backend use(Gson and javax.json) Standardise the json libraries used in the search bean
4 | User Distribution dashboard displays incorrect data against testing data | Admin Dashboard | High | SQL syntax is wrong, meanwhile, the database strucutre is note compatible with formet required by the dashboard
5
6
7
8
9
10

## Iteration 7
` | Bug Description | Bug Location | Severity | Notes
1 | Fuzzy word search in job search not supported as requested by the sponsor. e.g: "Financ Ex" does not pop up "Financial Executive" | User home page | Critical | Explore regex fuzzy match algorithms and libraries
2 | Track visualisation not displaying skills as the third level correct, the numbers are always limited to 3, there are more than three skills in most of the courses | Track Search Result | High | Check js file and java bean to find the bottleneck
3 | Clustered search result from the front end, unable to click "search other jobs" to go back to the home page | Track Search Result | Critical | Re-organize search result, add another search bar when user want to do a convenient search in the same page
4
5
6
7
8
9
10